CUSTOMER & MVP BLUEPRINT

AI Resume & Interview Coach  |  India (Phase 1)

Derived from Startup Validation Report — July 2026

# Executive Summary

This blueprint translates the Startup Validation Report's findings into a build-ready customer and MVP plan. The core problem — a widening gap between India's ~5M annual graduates and ~2.8M graduate-level jobs, with 60%+ of resumes failing ATS screening — is well-documented and severe. But the solution space is crowded: at least 8 funded or traction-proven competitors (PrepFree, Resumeera.xyz, ResumeGyani, Dovira AI, Jobcopy, Internshala, Kickresume, Novoresume) already serve this exact wedge in India, several with 100K–200K+ monthly active users.

No direct validation (users, interviews, payments) exists yet. This blueprint's MVP is therefore scoped deliberately narrow — a single niche segment, a manual/semi-automated build, and a 30-day path to real evidence — rather than a full-featured platform competing head-on with incumbents.

# Ideal Customer Profile

| Attribute | Profile |
| --- | --- |
| Life stage | Final-year student or graduate within 0–18 months of graduation |
| Education | Undergraduate degree from a tier-2/tier-3 Indian institution |
| Location | Non-metro India, reliable smartphone internet access |
| Income sensitivity | High — will pay ₹99–₹499 for proven outcomes, not vague subscriptions |
| Digital behaviour | YouTube, Instagram, WhatsApp/Telegram placement groups; Hinglish search |
| Core motivation | Get *any* interview call — driven by underconfidence, not career optimization |

# Buyer Persona

"Ankit, the Anxious Final-Year Applicant" Age 21 · B.Tech Mechanical, tier-3 college, UP · First-generation graduate Goal: Land any interview call before final semester ends. Frustration: Unsure resume format is correct; freezes in mock interviews; can't afford ₹5,000+ coaching. Willingness to pay: ₹99–₹299, only after peer proof — resists blind subscriptions.

# Top 10 Customer Pain Points

| # | Pain Point |
| --- | --- |
| 1 | Resume gets rejected before a human ever sees it (ATS filtering) |
| 2 | Freezes or rambles under real interview pressure |
| 3 | Doesn't know what recruiters actually look for |
| 4 | Can't afford professional resume writers or coaching institutes |
| 5 | Generic AI tools give Western-style advice, not Indian recruiter norms |
| 6 | Overwhelmed by conflicting advice across YouTube/forums |
| 7 | No accountability partner to actually practice interviews with |
| 8 | Can't tell if he's actually improving between attempts |
| 9 | Placement-cell support is generic, overloaded, and one-size-fits-all |
| 10 | Low confidence undermines performance even when skills are adequate |

# Customer Journey

| Stage | Trigger | Customer State | Opportunity |
| --- | --- | --- | --- |
| Awareness | Placement notice or rejection email | Anxious, searching YouTube/Google | Be visible in placement WhatsApp groups & YouTube shorts |
| Consideration | Compares free vs. paid tools | Price-sensitive, skeptical of AI | Free ATS score check as hook; peer testimonials |
| Purchase | Needs unlimited downloads / more mock rounds | Has seen value, considers paying | Low-friction ₹99–₹299 one-time unlock |
| Retention | Gets an interview call or offer | Grateful, likely to refer peers | Referral loop into next cohort + college relationship |

# Key Customer Objections

| Objection | Response |
| --- | --- |
| "Free tools already exist" | Lead with outcome proof (interview-call uplift), not features |
| "I don't trust AI on something this important" | Sample outputs + peer social proof + free trial |
| "I'll just ask ChatGPT for free" | India-specific ATS tuning + structured practice + progress tracking |
| "My college already has a placement cell" | Position as supplement, not replacement |

# Key Buying Triggers

- Placement season / campus drive announcements (highest intent)

- Just received a rejection or application ghosting

- A friend/senior got a call after using a similar tool

- College career cell recommends resume review before drive registration

# MVP Recommendation

## Build First

- AI/human-reviewed resume feedback + ATS score for ONE niche segment (e.g., tier-2/3 engineering students)

- A short, structured mock-interview question set with written feedback (voice/video optional later)

- Delivery via WhatsApp/Telegram + a simple landing page — no native app needed

- One-time ₹99–₹299 payment unlock (UPI) to test real willingness-to-pay

## Do NOT Build Yet

- Native mobile app

- Voice/video AI interview analysis

- Job-matching or job-board integration

- Multi-language / regional-language support

- B2B college dashboard or enterprise features

## Success Metrics

| Metric | Target (30 days) |
| --- | --- |
| Structured user interviews completed | 15–20 |
| Landing page → signup conversion | Clear signal (>10–15%) |
| Real payments collected (not stated intent) | ≥10 paying users |
| Institutional (college/placement-cell) conversations opened | ≥1 |

# MoSCoW Prioritization

| Must Have | AI/manual resume review + ATS score · Mock-interview question set with feedback · WhatsApp/Telegram delivery · UPI one-time payment · Single niche focus |
| --- | --- |
| Should Have | India-specific resume templates · Objection-handling content library · Simple referral mechanism |
| Could Have | Voice-based mock interviews · Progress-tracking dashboard · College partnership portal |
| Won't Have (MVP) | Native app · Multi-language support · Job-matching/marketplace · Enterprise B2B dashboard · Video interview analysis |

# Pricing Hypothesis

- Freemium entry: free ATS score check + 1 free mock question (acquisition hook, matches market price anchor already set by competitors)

- Core paid unlock: ₹99–₹299 one-time for full resume review + mock-interview set (matches target segment's proven willingness-to-pay)

- Avoid recurring subscription at launch — target segment resists blind subscriptions; validate with one-time purchases first

- Future B2B2C layer: per-student or flat licensing fee to colleges/placement cells once individual model is proven

# Top 5 Risks

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Funded, distribution-rich competitors (PrepFree, Resumeera) | High | High | Avoid head-on positioning; win a narrow niche + college channel first |
| Commoditized AI features | High | Medium | Moat via India-specific rubrics & trust, not raw AI capability |
| Low willingness-to-pay | Medium | High | Validate with real ₹ payments in Week 3, not survey answers |
| Side-project bandwidth limits speed | High | Medium | Timebox to 30 days; decide full-time commitment on real signal |
| AI advice accuracy for Indian recruiter norms | Medium | High | Human-in-the-loop review during early cohorts |

# 30-Day MVP Plan

| Week | Focus | Actions |
| --- | --- | --- |
| 1 | Talk to market | 15–20 structured interviews with final-year students/grads; map current tools & spend |
| 2 | Narrow niche & test demand | Pick one segment/college; build landing page; drive signups via network & WhatsApp |
| 3 | Ship Wizard-of-Oz MVP | Manually deliver resume review + mock feedback for 15–20 signups; charge ₹99–₹299 |
| 4 | Decide & plan | Review conversion/payment/feedback vs. Go/No-Go criteria; scope v1 or pivot |

# Founder Action Sheet — Top 10 Next Actions

| # | Action |
| --- | --- |
| 1 | Pick one niche segment (e.g., one tier-2/3 college or engineering branch) — write it down, commit |
| 2 | Interview 15–20 target students this week — ask about their last rejection, not opinions |
| 3 | Build a 1-page landing page describing the specific promise for that niche |
| 4 | Share it in 3–5 relevant WhatsApp/Telegram placement groups |
| 5 | Reach out to 1 college placement cell for a pilot conversation |
| 6 | Manually deliver resume review + mock interview feedback to first 10–20 signups |
| 7 | Charge a real ₹99–₹299 fee via UPI — do not give it away free |
| 8 | Track the same 2–3 pain points across interviews — confirm or kill the hypothesis |
| 9 | Collect 3–5 testimonials/referrals from satisfied early users |
| 10 | Review results against Go/No-Go criteria on Day 30 — decide before building more |

# Scores (0–100)

| Dimension | Score | Why |
| --- | --- | --- |
| Customer Clarity | 75 / 100 | ICP & persona well-defined; not yet confirmed with real interviews |
| Problem Severity | 85 / 100 | Backed by national labour data — structural, not anecdotal |
| PMF Potential | 45 / 100 | Real demand exists, but category is crowded with funded incumbents |
| MVP Readiness | 35 / 100 | Concept well-scoped, but zero users, interviews, or payments collected yet |

# Final Verdict

🟡 PROMISING BUT UNVALIDATED Strong, data-backed problem and clear customer profile — but zero direct evidence (users, interviews, payments) and a crowded competitive field. Run the 30-day MVP plan before further product investment.